## Instructions
Project Planner - MS Project-compatible Excel template
HOW IT WORKS
1. Settings | Set project start, working week (Mon-Sun Yes/No), hours/day, status date, Gantt scale and sprint calendar. Add holidays on 'Holidays'.
2. Resources | List people/roles with Max Units and hourly rate. They appear in the Resource dropdown on Tasks and in sprint capacity.
3. Tasks | One row per task. Enter Level (1 = phase/summary, 2 = task, 3 = sub-task...), Task Name, Duration in working days (0 = milestone), and up to two predecessors by ID with link type (FS, SS, FF, SF) and lag in days (negative = lead). A row becomes a SUMMARY automatically when the rows beneath it have a higher level; its dates, work, cost and progress roll up.
4. Track progress | Enter Actual Start, Actual Finish and % Complete. Forecast Start/Finish then use actuals and push every dependent task; Planned Start/Finish keep the original plan (= MS Project Baseline). Finish Variance and Status flag slippage.
5. Gantt | Read-only view: grey line = planned dates, green = done, blue = remaining on track, orange = remaining but late vs plan, dark = summary, red border = status date. Change GanttStart / GanttPeriod (1 = days, 7 = weeks) on Settings to scroll or zoom.
6. Sprints | Sprint calendar from Settings. Each task is tagged with the sprint its forecast start falls in. Work hours are prorated across sprints per resource, compared against capacity (Max Units x Hours/day x working days); over-allocations turn red.
7. Dashboard | KPIs, status counts, upcoming milestones and sprint load vs capacity.
CELL COLOURS
Blue text | Input - type here.
Black text on grey | Formula - do not overwrite. Summary rows grey-out inputs that are ignored.
Dark blue header | Input column. Dark grey header = calculated. Light grey header = helper column (hidden, grouped).
RULES (same as MS Project)
Task IDs | ID = sequence of named rows. Inserting a row renumbers IDs below it (like MS Project) - re-check predecessor IDs after inserting or deleting rows. Easiest: add new tasks at the bottom of a phase and set Level.
Outline levels | Each row's Level may be at most 1 higher than the row above. A '?' in WBS (red) means a level jump.
Predecessors | Link detail tasks, not summaries, and never link a task to itself or its own summary (that creates a circular reference). Summary rows ignore Duration / Predecessors / Actuals - they roll up.
Mode | Auto = scheduled from predecessors, project start and 'Start No Earlier Than'. Manual = pinned to the date in 'Start No Earlier Than / Manual Start'.
Rescheduling | Settings > RescheduleAfterStatus = Yes moves incomplete work to after the status date (like MS Project 'Update Project'), so late tasks push successors.
Capacity | Rows provided: 200 tasks, 50 resources, 26 sprints, 100 holidays. To extend, copy the last formula row down and extend the named ranges in Name Manager.
MOVING TO MICROSOFT PROJECT
One-time setting | MS Project > File > Options > Trust Center > Trust Center Settings > Legacy Formats > 'Allow loading files with legacy or non-default file formats'.
Import | In MS Project: File > Open > choose this .xlsx > Import Wizard > New map > 'As a new project' > tick Tasks (and Resources) > Tasks source worksheet = MSP_Tasks, Resources = MSP_Resources. Column headers already use MS Project field names, so the wizard maps them automatically.
Tip: Start/Finish | For auto-scheduled tasks map Duration + Predecessors (+ Constraint Type/Date) and set Start/Finish to '(not mapped)' - importing Start/Finish makes MS Project add fixed 'Start No Earlier Than' constraints. Map Baseline Start/Finish to keep the plan, and Actual Start/Finish/% Complete for progress.
Rows | MSP_Tasks contains 200 rows; blank rows import as blank tasks - delete them in MS Project or copy only the filled rows to a new sheet before importing.
From MS Project to Excel | MS Project > File > Save As > Excel Workbook > use the same field names, then paste Name / Outline Level / Duration / Predecessors etc. into the Tasks input columns (split '3FS+2d' into Pred ID, Type, Lag).
NAMED RANGES (Formulas > Name Manager)
Settings | ProjectStart, StatusDate, StatusWorkday, WorkWeek, Holidays, HoursPerDay, DefaultUnits, RescheduleAfterStatus, GanttStart, GanttPeriod, Sprint1Start, SprintLength, SprintCount, SprintPrefix, SprintLastEnd
Task columns | tsk_ID, tsk_WBS, tsk_Level, tsk_Name, tsk_Duration, tsk_PlanStart, tsk_PlanFinish, tsk_ActStart, tsk_ActFinish, tsk_FcStart, tsk_FcFinish, tsk_Variance, tsk_Progress, tsk_Status, tsk_Resource, tsk_Work, tsk_Cost, tsk_Sprint, tsk_Predecessors, tsk_IsSummary, tsk_IsLeaf ... and hdr_* anchors used by OFFSET look-ups
Resources / Sprints | res_Name, res_MaxUnits, res_Rate, ... spr_Name, spr_Start, spr_End, spr_Capacity, spr_Work
Key formulas | Planned Start = WORKDAY.INTL(MAX(ProjectStart, StartNoEarlierThan, predecessor drivers) - 1, 1, WorkWeek, Holidays). Pred driver (FS) = WORKDAY.INTL(OFFSET(hdr_PlanFinish, MATCH(PredID, tsk_ID, 0), 0), 1 + Lag, WorkWeek, Holidays). Summary Start = MIN of its descendant block (OFFSET from the row, height = Descendant Count via COUNTIF(tsk_WBS, WBS & ".*")).

## Dashboard
Customer Portal Implementation - Dashboard
Project manager: Priya Sharma Status date: Sun 25-Oct-2026
| Key indicator | Value | Status (detail tasks) | Count
| Planned start | 2026-09-07 | Complete | 9
| Planned finish | 2027-01-06 | In Progress | 0
| Forecast finish | 2027-01-06 | Behind | 2
| Finish variance (work days) | 0 | Late Start | 1
| Overall progress (duration-weighted) | 43.42% | Not Started | 11
| Planned progress by status date | 45.43%
| Detail tasks | 23
| Milestones | 5
| Total work (hrs) | 720
| Total cost | 58040
| Current sprint | Sprint 4
| Next milestones (forecast) | Forecast date
| Build complete | 2026-11-09
| Go-live | 2026-12-15
| Project closed | 2027-01-06

## Settings
Project Settings
Blue = edit me. Grey = calculated. Column D shows the named range every formula uses.
| Setting | Value | Named range | Notes
| Project name | Customer Portal Implementation | ProjectName | Shown on every sheet title.
| Project manager | Priya Sharma | ProjectManager
| Project start date | 2026-09-07 | ProjectStart | Tasks without predecessors start here (moved to the next working day if needed).
| Status date override |  | StatusDateOverride | Leave blank to use TODAY(). Type a date to report progress 'as of' that day.
| Status date (in use) | 2026-10-25 | StatusDate | Drives Status, the red 'today' line on the Gantt and rescheduling of late work.
| First working day on/after status date | 2026-10-26 | StatusWorkday
| Reschedule incomplete work after status date? | Yes | RescheduleAfterStatus | Yes = like MS Project 'move incomplete parts after status date': unstarted tasks can't start before the status date and in-progress tasks finish their remaining duration after it, pushing all successors.
| Working hours per day | 8 | HoursPerDay | Work (hrs) = Duration x Hours/day x Units.
| Default assignment units | 100% | DefaultUnits | Used when a task has a resource but Units is blank. 100% = full time.
| Monday is a working day | Yes | WorkMon | Working-week calendar (Yes/No). Feeds every WORKDAY / NETWORKDAYS formula.
| Tuesday is a working day | Yes | WorkTue
| Wednesday is a working day | Yes | WorkWed
| Thursday is a working day | Yes | WorkThu
| Friday is a working day | Yes | WorkFri
| Saturday is a working day | No | WorkSat
| Sunday is a working day | No | WorkSun
| Weekend mask (calculated) | 0000011 | WorkWeek | 7-character Mon..Sun string used by WORKDAY.INTL (1 = non-working).
| Gantt timeline start | 2026-09-07 | GanttStart | Defaults to the Monday of the project start week. Overwrite with any date to scroll the timeline.
| Gantt days per column | 1 | GanttPeriod | 1 = daily timeline, 7 = weekly timeline (150 columns either way).
| Sprint 1 start date | 2026-09-07 | Sprint1Start | Defaults to the project start. Overwrite to align with your sprint calendar.
| Sprint length (calendar days) | 14 | SprintLength | 14 = two-week sprints.
| Number of sprints | 12 | SprintCount | Up to 26. Tasks outside the sprint range are labelled 'Backlog'.
| Sprint name prefix | Sprint | SprintPrefix | Sprint names = prefix & number.
| Last sprint end (calculated) | 2027-02-21 | SprintLastEnd

## Tasks
Customer Portal Implementation - Task Entry
Type in BLUE columns only. Level = outline level (1 = phase, 2 = task, 3 = sub-task). Planned dates come from Duration + Predecessors; Forecast dates also use Actuals, so slips ripple to every successor.
IDENTITY |  |  |  | SCHEDULING INPUTS | [8 empty] | PLAN / ACTUAL / FORECAST | [6 empty] | PROGRESS |  |  | RESOURCES & SPRINT | [6 empty] | HELPER COLUMNS (hidden - click + above to show)
ID | WBS | Level | Task Name | Mode | Duration (work days) | Pred 1 ID | Type 1 | Lag 1 (days) | Pred 2 ID | Type 2 | Lag 2 (days) | Start No Earlier Than / Manual Start | Planned Start | Planned Finish | Actual Start | Actual Finish | Forecast Start | Forecast Finish | Finish Variance (work days) | % Complete (enter) | Progress % (rolled up) | Status | Resource | Units | Work (hrs) | Cost | Sprint | Predecessors (MSP format) | Notes | Lvl (effective) | Row Index | Parent Row | Descendant Count | Is Summary | Is Leaf | Pred1 Plan Driver | Pred2 Plan Driver | Pred1 Fcst Driver | Pred2 Fcst Driver | Fcst Start # (leaf) | Fcst Finish # (leaf) | Work per Cal Day | Weight Dur | Weight Done | Pred1 Text | Pred2 Text | Open Milestone Key
1 | 1 | 1 | Initiation | Auto | [8 empty] | 2026-09-07 | 2026-09-11 |  |  | 2026-09-07 | 2026-09-14 | 1 |  | 100% | Complete |  |  | 40 | 3400 |  |  | Phase 1 - summary rows roll up dates, work, cost and progress automatically. | 1 | 1 | 0 | 3 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 1.1 | 2 | Project charter & scope statement | Auto | 3 | [7 empty] | 2026-09-07 | 2026-09-09 | 2026-09-07 | 2026-09-10 | 2026-09-07 | 2026-09-10 | 1 | 100% | 100% | Complete | Priya Sharma |  | 24 | 2280 | Sprint 1 |  | Took 1 extra day for sponsor sign-off. | 2 | 2 | 6 | 0 | FALSE | 1 | 0 | 0 | 0 | 0 | 2026-09-07 | 2026-09-10 | 6 | 3 | 3
3 | 1.2 | 2 | Stakeholder kickoff workshop | Auto | 2 | 2 | FS | [5 empty] | 2026-09-10 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-11 | 2026-09-14 | 1 | 100% | 100% | Complete | Morgan Patel |  | 16 | 1120 | Sprint 1 | 2 |  | 2 | 3 | 6 | 0 | FALSE | 1 | 2026-09-10 | 0 | 2026-09-11 | 0 | 2026-09-11 | 2026-09-14 | 4 | 2 | 2 | 2
4 | 1.3 | 2 | Kickoff complete | Auto | 0 | 3 | FS | [5 empty] | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 1 | 100% | 100% | Complete |  |  | 0 | 0 | Sprint 1 | 3 | Milestone (Duration 0). | 2 | 4 | 6 | 0 | FALSE | 1 | 2026-09-11 | 0 | 2026-09-14 | 0 | 2026-09-14 | 2026-09-14 | 0 | 0.1 | 0.1 | 3
5 | 2 | 1 | Requirements & Design | Auto | [8 empty] | 2026-09-14 | 2026-10-01 |  |  | 2026-09-15 | 2026-10-06 | 3 |  | 100% | Complete |  |  | 152 | 12480 |  |  |  | 1 | 5 | 0 | 4 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 2.1 | 2 | Requirements gathering | Auto | 8 | 4 | FS | [5 empty] | 2026-09-14 | 2026-09-23 | 2026-09-15 | 2026-09-25 | 2026-09-15 | 2026-09-25 | 2 | 100% | 100% | Complete | Morgan Patel |  | 64 | 4480 | Sprint 1 | 4 |  | 2 | 6 | 10 | 0 | FALSE | 1 | 2026-09-14 | 0 | 2026-09-15 | 0 | 2026-09-15 | 2026-09-25 | 5.8182 | 8 | 8 | 4
7 | 2.2 | 2 | Solution architecture | Auto | 5 | 6 | SS | 3 |  |  |  |  | 2026-09-17 | 2026-09-23 | 2026-09-18 | 2026-09-25 | 2026-09-18 | 2026-09-25 | 2 | 100% | 100% | Complete | Alex Chen |  | 40 | 4400 | Sprint 1 | 6SS+3d | Start-to-Start + 3 day lag example. | 2 | 7 | 10 | 0 | FALSE | 1 | 2026-09-17 | 0 | 2026-09-18 | 0 | 2026-09-18 | 2026-09-25 | 5 | 5 | 5 | 6SS+3d
8 | 2.3 | 2 | UX wireframes & prototype | Auto | 6 | 6 | FS | [5 empty] | 2026-09-24 | 2026-10-01 | 2026-09-28 | 2026-10-06 | 2026-09-28 | 2026-10-06 | 3 | 100% | 100% | Complete | Casey Kim |  | 48 | 3600 | Sprint 2 | 6 |  | 2 | 8 | 10 | 0 | FALSE | 1 | 2026-09-24 | 0 | 2026-09-28 | 0 | 2026-09-28 | 2026-10-06 | 5.3333 | 6 | 6 | 6
9 | 2.4 | 2 | Design sign-off | Auto | 0 | 7 | FS |  | 8 | FS |  |  | 2026-10-01 | 2026-10-01 | 2026-10-06 | 2026-10-06 | 2026-10-06 | 2026-10-06 | 3 | 100% | 100% | Complete |  |  | 0 | 0 | Sprint 3 | 7,8 | Two predecessors - waits for the later one. | 2 | 9 | 10 | 0 | FALSE | 1 | 2026-09-23 | 2026-10-01 | 2026-09-25 | 2026-10-06 | 2026-10-06 | 2026-10-06 | 0 | 0.1 | 0.1 | 7 | 8
10 | 3 | 1 | Build | Auto | [8 empty] | 2026-10-02 | 2026-10-30 |  |  | 2026-10-07 | 2026-11-09 | 6 |  | 45.13% | Behind |  |  | 324 | 26700 |  |  |  | 1 | 10 | 0 | 9 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 3.1 | 2 | Backend | Auto | [8 empty] | 2026-10-02 | 2026-10-30 |  |  | 2026-10-07 | 2026-11-09 | 6 |  | 47.62% | Behind |  |  | 168 | 14280 |  |  | Level-2 summary with sub-tasks. | 2 | 11 | 15 | 3 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 3.1.1 | 3 | Data model & database setup | Auto | 5 | 9 | FS | [5 empty] | 2026-10-02 | 2026-10-08 | 2026-10-07 | 2026-10-14 | 2026-10-07 | 2026-10-14 | 4 | 100% | 100% | Complete | Jordan Lee |  | 40 | 3400 | Sprint 3 | 9 |  | 3 | 12 | 16 | 0 | FALSE | 1 | 2026-10-02 | 0 | 2026-10-07 | 0 | 2026-10-07 | 2026-10-14 | 5 | 5 | 5 | 9
13 | 3.1.2 | 3 | Core API endpoints | Auto | 10 | 12 | FS | [5 empty] | 2026-10-09 | 2026-10-22 | 2026-10-15 |  | 2026-10-15 | 2026-10-30 | 6 | 50% | 50% | Behind | Jordan Lee |  | 80 | 6800 | Sprint 3 | 12 | In progress - enter % Complete; forecast finish adjusts. | 3 | 13 | 16 | 0 | FALSE | 1 | 2026-10-09 | 0 | 2026-10-15 | 0 | 2026-10-15 | 2026-10-30 | 5 | 10 | 5 | 12
14 | 3.1.3 | 3 | Payment gateway integration | Auto | 6 | 13 | FS | [5 empty] | 2026-10-23 | 2026-10-30 |  |  | 2026-11-02 | 2026-11-09 | 6 |  | 0% | Late Start | Jordan Lee |  | 48 | 4080 | Sprint 5 | 13 |  | 3 | 14 | 16 | 0 | FALSE | 1 | 2026-10-23 | 0 | 2026-11-02 | 0 | 2026-11-02 | 2026-11-09 | 6 | 6 | 0 | 13
15 | 3.2 | 2 | Frontend | Auto | [8 empty] | 2026-10-02 | 2026-10-29 |  |  | 2026-10-07 | 2026-11-06 | 6 |  | 42.86% | Behind |  |  | 156 | 12420 |  |  |  | 2 | 15 | 15 | 3 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 3.2.1 | 3 | UI component library | Auto | 6 | 9 | FS | [5 empty] | 2026-10-02 | 2026-10-09 | 2026-10-07 | 2026-10-16 | 2026-10-07 | 2026-10-16 | 5 | 100% | 100% | Complete | Sam Rivera |  | 48 | 3840 | Sprint 3 | 9 |  | 3 | 16 | 20 | 0 | FALSE | 1 | 2026-10-02 | 0 | 2026-10-07 | 0 | 2026-10-07 | 2026-10-16 | 4.8 | 6 | 6 | 9
17 | 3.2.2 | 3 | Feature screens | Auto | 12 | 16 | FS |  | 13 | SS | 2 |  | 2026-10-13 | 2026-10-28 | 2026-10-19 |  | 2026-10-19 | 2026-11-05 | 6 | 25% | 25% | Behind | Sam Rivera |  | 96 | 7680 | Sprint 4 | 16,13SS+2d |  | 3 | 17 | 20 | 0 | FALSE | 1 | 2026-10-12 | 2026-10-13 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-11-05 | 5.3333 | 12 | 3 | 16 | 13SS+2d
18 | 3.2.3 | 3 | Accessibility review | Auto | 3 | 17 | FF | 1 |  |  |  |  | 2026-10-27 | 2026-10-29 |  |  | 2026-11-04 | 2026-11-06 | 6 |  | 0% | Not Started | Casey Kim | 50% | 12 | 900 | Sprint 5 | 17FF+1d | Finish-to-Finish + 1 day; 50% units. | 3 | 18 | 20 | 0 | FALSE | 1 | 2026-10-27 | 0 | 2026-11-04 | 0 | 2026-11-04 | 2026-11-06 | 4 | 3 | 0 | 17FF+1d
19 | 3.3 | 2 | Build complete | Auto | 0 | 14 | FS |  | 18 | FS |  |  | 2026-10-30 | 2026-10-30 |  |  | 2026-11-09 | 2026-11-09 | 6 |  | 0% | Not Started |  |  | 0 | 0 | Sprint 5 | 14,18 | Milestone | 2 | 19 | 15 | 0 | FALSE | 1 | 2026-10-30 | 2026-10-29 | 2026-11-09 | 2026-11-06 | 2026-11-09 | 2026-11-09 | 0 | 0.1 | 0 | 14 | 18 | 2026-11-09
20 | 4 | 1 | Test & Release | Auto | [8 empty] | 2026-11-02 | 2027-01-04 |  |  | 2026-11-10 | 2027-01-04 | 0 |  | 0% | Not Started |  |  | 180 | 13180 |  |  |  | 1 | 20 | 0 | 6 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 4.1 | 2 | System integration testing | Auto | 8 | 19 | FS | [5 empty] | 2026-11-02 | 2026-11-11 |  |  | 2026-11-10 | 2026-11-19 | 6 |  | 0% | Not Started | Taylor Morgan |  | 64 | 4160 | Sprint 5 | 19 |  | 2 | 21 | 25 | 0 | FALSE | 1 | 2026-11-02 | 0 | 2026-11-10 | 0 | 2026-11-10 | 2026-11-19 | 6.4 | 8 | 0 | 19
22 | 4.2 | 2 | User acceptance testing | Auto | 6 | 21 | FS |  |  |  |  | 2026-12-07 | 2026-12-07 | 2026-12-14 |  |  | 2026-12-07 | 2026-12-14 | 0 |  | 0% | Not Started | Morgan Patel |  | 48 | 3360 | Sprint 7 | 21 | Start No Earlier Than 07-Dec (client availability). | 2 | 22 | 25 | 0 | FALSE | 1 | 2026-11-12 | 0 | 2026-11-20 | 0 | 2026-12-07 | 2026-12-14 | 6 | 6 | 0 | 21
23 | 4.3 | 2 | Training & user guides | Auto | 5 | 21 | SS | 2 |  |  |  |  | 2026-11-04 | 2026-11-10 |  |  | 2026-11-12 | 2026-11-18 | 6 |  | 0% | Not Started | Casey Kim | 50% | 20 | 1500 | Sprint 5 | 21SS+2d |  | 2 | 23 | 25 | 0 | FALSE | 1 | 2026-11-04 | 0 | 2026-11-12 | 0 | 2026-11-12 | 2026-11-18 | 2.8571 | 5 | 0 | 21SS+2d
24 | 4.4 | 2 | Go-live readiness review | Auto | 1 | 22 | FS |  | 23 | FS |  |  | 2026-12-15 | 2026-12-15 |  |  | 2026-12-15 | 2026-12-15 | 0 |  | 0% | Not Started | Priya Sharma |  | 8 | 760 | Sprint 8 | 22,23 |  | 2 | 24 | 25 | 0 | FALSE | 1 | 2026-12-15 | 2026-11-11 | 2026-12-15 | 2026-11-19 | 2026-12-15 | 2026-12-15 | 8 | 1 | 0 | 22 | 23
25 | 4.5 | 2 | Go-live | Auto | 0 | 24 | FS | [5 empty] | 2026-12-15 | 2026-12-15 |  |  | 2026-12-15 | 2026-12-15 | 0 |  | 0% | Not Started |  |  | 0 | 0 | Sprint 8 | 24 | Milestone | 2 | 25 | 25 | 0 | FALSE | 1 | 2026-12-15 | 0 | 2026-12-15 | 0 | 2026-12-15 | 2026-12-15 | 0 | 0.1 | 0 | 24 |  | 2026-12-15
26 | 4.6 | 2 | Hypercare support | Auto | 10 | 25 | FS | [5 empty] | 2026-12-16 | 2027-01-04 |  |  | 2026-12-16 | 2027-01-04 | 0 |  | 0% | Not Started | Jordan Lee | 50% | 40 | 3400 | Sprint 8 | 25 |  | 2 | 26 | 25 | 0 | FALSE | 1 | 2026-12-16 | 0 | 2026-12-16 | 0 | 2026-12-16 | 2027-01-04 | 2 | 10 | 0 | 25
27 | 5 | 1 | Project Close | Auto | [8 empty] | 2026-11-16 | 2027-01-06 |  |  | 2026-11-16 | 2027-01-06 | 0 |  | 0% | Not Started |  |  | 24 | 2280 |  |  |  | 1 | 27 | 0 | 3 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 5.1 | 2 | Steering committee update | Manual | 1 | [6 empty] | 2026-11-16 | 2026-11-16 | 2026-11-16 |  |  | 2026-11-16 | 2026-11-16 | 0 |  | 0% | Not Started | Priya Sharma |  | 8 | 760 | Sprint 6 |  | Manual mode example: fixed on the date in the Start No Earlier Than / Manual Start column. | 2 | 28 | 32 | 0 | FALSE | 1 | 0 | 0 | 0 | 0 | 2026-11-16 | 2026-11-16 | 8 | 1 | 0
29 | 5.2 | 2 | Lessons learned | Auto | 2 | 26 | FS | [5 empty] | 2027-01-05 | 2027-01-06 |  |  | 2027-01-05 | 2027-01-06 | 0 |  | 0% | Not Started | Priya Sharma |  | 16 | 1520 | Sprint 9 | 26 |  | 2 | 29 | 32 | 0 | FALSE | 1 | 2027-01-05 | 0 | 2027-01-05 | 0 | 2027-01-05 | 2027-01-06 | 8 | 2 | 0 | 26
30 | 5.3 | 2 | Project closed | Auto | 0 | 29 | FS | [5 empty] | 2027-01-06 | 2027-01-06 |  |  | 2027-01-06 | 2027-01-06 | 0 |  | 0% | Not Started |  |  | 0 | 0 | Sprint 9 | 29 | Milestone | 2 | 30 | 32 | 0 | FALSE | 1 | 2027-01-06 | 0 | 2027-01-06 | 0 | 2027-01-06 | 2027-01-06 | 0 | 0.1 | 0 | 29 |  | 2027-01-06
[31 empty] | 31 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 32 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 33 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 34 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 35 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 36 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 37 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 38 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 39 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 40 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 41 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 42 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 43 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 44 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 45 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 46 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 47 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 48 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 49 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 50 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 51 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 52 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 53 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 54 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 55 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 56 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 57 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 58 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 59 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 60 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 61 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 62 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 63 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 64 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 65 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 66 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 67 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 68 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 69 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 70 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 71 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 72 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 73 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 74 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 75 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 76 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 77 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 78 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 79 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 80 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 81 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 82 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 83 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 84 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 85 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 86 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 87 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 88 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 89 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 90 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 91 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 92 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 93 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 94 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 95 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 96 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 97 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 98 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 99 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 100 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 101 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 102 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 103 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 104 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 105 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 106 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 107 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 108 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 109 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 110 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 111 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 112 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 113 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 114 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 115 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 116 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 117 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 118 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 119 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 120 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 121 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 122 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 123 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 124 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 125 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 126 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 127 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 128 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 129 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 130 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 131 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 132 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 133 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 134 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 135 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 136 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 137 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 138 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 139 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 140 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 141 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 142 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 143 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 144 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 145 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 146 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 147 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 148 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 149 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 150 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 151 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 152 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 153 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 154 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 155 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 156 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 157 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 158 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 159 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 160 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 161 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 162 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 163 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 164 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 165 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 166 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 167 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 168 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 169 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 170 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 171 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 172 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 173 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 174 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 175 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 176 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 177 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 178 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 179 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 180 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 181 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 182 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 183 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 184 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 185 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 186 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 187 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 188 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 189 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 190 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 191 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 192 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 193 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 194 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 195 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 196 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 197 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 198 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 199 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 200 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
PLAN / ACTUAL / FORECAST = IF([Task Name]="","",IF([Is Summary],MIN(OFFSET(hdr_PlanStart,[Row Index]+1,0,[Descendant Count],1)),IF([SCHEDULING INPUTS]="Manual",IF(N([Start No Earlier Than / Manual Start])>0,[Start No Earlier Than / Manual Start],ProjectStart),WORKDAY.INTL(MAX(ProjectStart,N([Start No Earlier Than / Manual Start]),[Pred1 Plan Driver],[Pred2 Plan Driver])-1,1,WorkWeek,Holidays))))
Planned Finish = IF([Task Name]="","",IF([Is Summary],MAX(OFFSET(hdr_PlanFinish,[Row Index]+1,0,[Descendant Count],1)),IF(N([Duration (work days)])<=0,[PLAN / ACTUAL / FORECAST],WORKDAY.INTL([PLAN / ACTUAL / FORECAST],[Duration (work days)]-1,WorkWeek,Holidays))))
Finish Variance (work days) = IF([Task Name]="","",IF([Forecast Finish]>=[Planned Finish],NETWORKDAYS.INTL([Planned Finish],[Forecast Finish],WorkWeek,Holidays)-1,1-NETWORKDAYS.INTL([Forecast Finish],[Planned Finish],WorkWeek,Holidays)))
Fcst Start # (leaf) = IF([Is Leaf]=1,[Forecast Start],0)
Fcst Finish # (leaf) = IF([Is Leaf]=1,[Forecast Finish],0)
Open Milestone Key = IF(AND([Is Leaf]=1,N([Duration (work days)])=0,[Progress % (rolled up)]<1),[Forecast Finish]+[Row Index]/100000,"")

## Gantt
Customer Portal Implementation - Gantt Chart | [17 empty] | ━ | Planned dates (line) | [11 empty] | Done (% complete) | [11 empty] | Remaining - on track | [11 empty] | Remaining - late vs plan
Status date: Sun 25-Oct-2026 ¦ Forecast finish: 06-Jan-2027 ¦ Planned finish: 06-Jan-2027 | [18 empty] | Summary (forecast) | [10 empty] | ◆ | Forecast milestone (red = late) | [10 empty] | ◇ | Planned milestone | [11 empty] | Red column = status date; grey = non-working
[18 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
[18 empty] | Sep | '26 | [22 empty] | Oct | '26 | [29 empty] | Nov | '26 | [28 empty] | Dec | '26 | [29 empty] | Jan | '27 | [29 empty] | Feb | '27
ID | WBS | Task Name | Dur | Planned Start | Planned Finish | Fcst / Act Start | Fcst / Act Finish | % | Resource | Status | IsSum | IsMile | Done From | Done To | Rem From | Rem To | Late | time axis 2026-09-07 to 2027-02-03
1 | 1 | Initiation | 6 | 2026-09-07 | 2026-09-11 | 2026-09-07 | 2026-09-14 | 100% |  | Complete | TRUE | FALSE | 0 | 0 | 0 | 0 | TRUE | bar: 2026-09-07 to 2026-09-11
2 | 1.1 | Project charter & scope statement | 3 | 2026-09-07 | 2026-09-09 | 2026-09-07 | 2026-09-10 | 100% | Priya Sharma | Complete | FALSE | FALSE | 2026-09-07 | 2026-09-10 | 0 | 0 | TRUE | bar: 2026-09-07 to 2026-09-09
3 | 1.2 | Stakeholder kickoff workshop | 2 | 2026-09-10 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 100% | Morgan Patel | Complete | FALSE | FALSE | 2026-09-11 | 2026-09-14 | 0 | 0 | TRUE | bar: 2026-09-10 to 2026-09-11
4 | 1.3 | Kickoff complete | 0 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-14 | 100% |  | Complete | FALSE | TRUE | 0 | 0 | 0 | 0 | TRUE | bar: 2026-09-11; 2026-09-14
5 | 2 | Requirements & Design | 16 | 2026-09-14 | 2026-10-01 | 2026-09-15 | 2026-10-06 | 100% |  | Complete | TRUE | FALSE | 0 | 0 | 0 | 0 | TRUE | bar: 2026-09-14 to 2026-10-01
6 | 2.1 | Requirements gathering | 8 | 2026-09-14 | 2026-09-23 | 2026-09-15 | 2026-09-25 | 100% | Morgan Patel | Complete | FALSE | FALSE | 2026-09-15 | 2026-09-25 | 0 | 0 | TRUE | bar: 2026-09-14 to 2026-09-23
7 | 2.2 | Solution architecture | 5 | 2026-09-17 | 2026-09-23 | 2026-09-18 | 2026-09-25 | 100% | Alex Chen | Complete | FALSE | FALSE | 2026-09-18 | 2026-09-25 | 0 | 0 | TRUE | bar: 2026-09-17 to 2026-09-23
8 | 2.3 | UX wireframes & prototype | 6 | 2026-09-24 | 2026-10-01 | 2026-09-28 | 2026-10-06 | 100% | Casey Kim | Complete | FALSE | FALSE | 2026-09-28 | 2026-10-06 | 0 | 0 | TRUE | bar: 2026-09-24 to 2026-10-01
9 | 2.4 | Design sign-off | 0 | 2026-10-01 | 2026-10-01 | 2026-10-06 | 2026-10-06 | 100% |  | Complete | FALSE | TRUE | 0 | 0 | 0 | 0 | TRUE | bar: 2026-10-01; 2026-10-06
10 | 3 | Build | 24 | 2026-10-02 | 2026-10-30 | 2026-10-07 | 2026-11-09 | 45.13% |  | Behind | TRUE | FALSE | 0 | 0 | 0 | 0 | TRUE | bar: 2026-10-02 to 2026-10-30
11 | 3.1 | Backend | 24 | 2026-10-02 | 2026-10-30 | 2026-10-07 | 2026-11-09 | 47.62% |  | Behind | TRUE | FALSE | 0 | 0 | 0 | 0 | TRUE | bar: 2026-10-02 to 2026-10-30
12 | 3.1.1 | Data model & database setup | 5 | 2026-10-02 | 2026-10-08 | 2026-10-07 | 2026-10-14 | 100% | Jordan Lee | Complete | FALSE | FALSE | 2026-10-07 | 2026-10-14 | 0 | 0 | TRUE | bar: 2026-10-02 to 2026-10-08
13 | 3.1.2 | Core API endpoints | 10 | 2026-10-09 | 2026-10-22 | 2026-10-15 | 2026-10-30 | 50% | Jordan Lee | Behind | FALSE | FALSE | 2026-10-15 | 2026-10-22 | 2026-10-23 | 2026-10-30 | TRUE | bar: 2026-10-09 to 2026-10-22
14 | 3.1.3 | Payment gateway integration | 6 | 2026-10-23 | 2026-10-30 | 2026-11-02 | 2026-11-09 | 0% | Jordan Lee | Late Start | FALSE | FALSE | 0 | 0 | 2026-11-02 | 2026-11-09 | TRUE | bar: 2026-10-23 to 2026-10-30
15 | 3.2 | Frontend | 23 | 2026-10-02 | 2026-10-29 | 2026-10-07 | 2026-11-06 | 42.86% |  | Behind | TRUE | FALSE | 0 | 0 | 0 | 0 | TRUE | bar: 2026-10-02 to 2026-10-29
16 | 3.2.1 | UI component library | 6 | 2026-10-02 | 2026-10-09 | 2026-10-07 | 2026-10-16 | 100% | Sam Rivera | Complete | FALSE | FALSE | 2026-10-07 | 2026-10-16 | 0 | 0 | TRUE | bar: 2026-10-02 to 2026-10-09
17 | 3.2.2 | Feature screens | 12 | 2026-10-13 | 2026-10-28 | 2026-10-19 | 2026-11-05 | 25% | Sam Rivera | Behind | FALSE | FALSE | 2026-10-19 | 2026-10-23 | 2026-10-24 | 2026-11-05 | TRUE | bar: 2026-10-13 to 2026-10-28
18 | 3.2.3 | Accessibility review | 3 | 2026-10-27 | 2026-10-29 | 2026-11-04 | 2026-11-06 | 0% | Casey Kim | Not Started | FALSE | FALSE | 0 | 0 | 2026-11-04 | 2026-11-06 | TRUE | bar: 2026-10-27 to 2026-10-29
19 | 3.3 | Build complete | 0 | 2026-10-30 | 2026-10-30 | 2026-11-09 | 2026-11-09 | 0% |  | Not Started | FALSE | TRUE | 0 | 0 | 0 | 0 | TRUE | bar: 2026-10-30; 2026-11-09
20 | 4 | Test & Release | 36 | 2026-11-02 | 2027-01-04 | 2026-11-10 | 2027-01-04 | 0% |  | Not Started | TRUE | FALSE | 0 | 0 | 0 | 0 | FALSE | bar: 2026-11-02 to 2027-01-04
21 | 4.1 | System integration testing | 8 | 2026-11-02 | 2026-11-11 | 2026-11-10 | 2026-11-19 | 0% | Taylor Morgan | Not Started | FALSE | FALSE | 0 | 0 | 2026-11-10 | 2026-11-19 | TRUE | bar: 2026-11-02 to 2026-11-11
22 | 4.2 | User acceptance testing | 6 | 2026-12-07 | 2026-12-14 | 2026-12-07 | 2026-12-14 | 0% | Morgan Patel | Not Started | FALSE | FALSE | 0 | 0 | 2026-12-07 | 2026-12-14 | FALSE | bar: 2026-12-07 to 2026-12-14
23 | 4.3 | Training & user guides | 5 | 2026-11-04 | 2026-11-10 | 2026-11-12 | 2026-11-18 | 0% | Casey Kim | Not Started | FALSE | FALSE | 0 | 0 | 2026-11-12 | 2026-11-18 | TRUE | bar: 2026-11-04 to 2026-11-10
24 | 4.4 | Go-live readiness review | 1 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 0% | Priya Sharma | Not Started | FALSE | FALSE | 0 | 0 | 2026-12-15 | 2026-12-15 | FALSE | bar: 2026-12-15
25 | 4.5 | Go-live | 0 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 0% |  | Not Started | FALSE | TRUE | 0 | 0 | 0 | 0 | FALSE | bar: 2026-12-15
26 | 4.6 | Hypercare support | 10 | 2026-12-16 | 2027-01-04 | 2026-12-16 | 2027-01-04 | 0% | Jordan Lee | Not Started | FALSE | FALSE | 0 | 0 | 2026-12-16 | 2027-01-04 | FALSE | bar: 2026-12-16 to 2027-01-04
27 | 5 | Project Close | 34 | 2026-11-16 | 2027-01-06 | 2026-11-16 | 2027-01-06 | 0% |  | Not Started | TRUE | FALSE | 0 | 0 | 0 | 0 | FALSE | bar: 2026-11-16 to 2027-01-06
28 | 5.1 | Steering committee update | 1 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 0% | Priya Sharma | Not Started | FALSE | FALSE | 0 | 0 | 2026-11-16 | 2026-11-16 | FALSE | bar: 2026-11-16
29 | 5.2 | Lessons learned | 2 | 2027-01-05 | 2027-01-06 | 2027-01-05 | 2027-01-06 | 0% | Priya Sharma | Not Started | FALSE | FALSE | 0 | 0 | 2027-01-05 | 2027-01-06 | FALSE | bar: 2027-01-05 to 2027-01-06
30 | 5.3 | Project closed | 0 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 0% |  | Not Started | FALSE | TRUE | 0 | 0 | 0 | 0 | FALSE | bar: 2027-01-06
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE
[11 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE

## Resources
Resource Sheet
Like MS Project's Resource Sheet. Names here feed the Resource dropdown on Tasks.
| Resource Name | Initials | Group / Role | Type | Max Units | Std Rate / hr | Email | # Tasks | Assigned Work (hrs) | Assigned Cost | Notes
| Priya Sharma | PS | Project Manager | Work | 50% | 95 | priya@example.com | 4 | 56 | 5320
| Morgan Patel | MP | Business Analyst | Work | 100% | 70 | morgan@example.com | 3 | 128 | 8960
| Alex Chen | AC | Solution Architect | Work | 50% | 110 | alex@example.com | 1 | 40 | 4400
| Casey Kim | CK | UX Designer | Work | 100% | 75 | casey@example.com | 3 | 80 | 6000
| Jordan Lee | JL | Backend Developer | Work | 100% | 85 | jordan@example.com | 4 | 208 | 17680
| Sam Rivera | SR | Frontend Developer | Work | 100% | 80 | sam@example.com | 2 | 144 | 11520
| Taylor Morgan | TM | QA Engineer | Work | 100% | 65 | taylor@example.com | 1 | 64 | 4160

## Sprints
Customer Portal Implementation - Sprint & Capacity Planning
Sprint calendar is generated from Settings (Sprint1Start, SprintLength, SprintCount). Work is prorated across sprints by the calendar days each task's forecast dates overlap the sprint.
# | Sprint | Start | End | Working Days | Sprint Goal | Tasks Starting | Planned Work (hrs) | Team Capacity (hrs) | Utilisation | Status
1 | Sprint 1 | 2026-09-07 | 2026-09-20 | 10 | Charter & kickoff | 5 | 89.9091 | 480 | 18.73% | Closed
2 | Sprint 2 | 2026-09-21 | 2026-10-04 | 10 | Requirements | 1 | 91.4242 | 480 | 19.05% | Closed
3 | Sprint 3 | 2026-10-05 | 2026-10-18 | 10 | Design & architecture | 4 | 118.6667 | 480 | 24.72% | Closed
4 | Sprint 4 | 2026-10-19 | 2026-11-01 | 10 | Foundations: DB + components | 1 | 134.6667 | 480 | 28.06% | Active
5 | Sprint 5 | 2026-11-02 | 2026-11-15 | 10 | Core APIs + screens | 5 | 131.1619 | 480 | 27.33% | Future
6 | Sprint 6 | 2026-11-16 | 2026-11-29 | 10 | Payments + screens | 1 | 42.1714 | 480 | 8.786% | Future
7 | Sprint 7 | 2026-11-30 | 2026-12-13 | 10 | Feature complete | 1 | 42 | 480 | 8.75% | Future
8 | Sprint 8 | 2026-12-14 | 2026-12-27 | 8 | System testing | 3 | 38 | 384 | 9.896% | Future
9 | Sprint 9 | 2026-12-28 | 2027-01-10 | 8 | UAT | 2 | 32 | 384 | 8.333% | Future
10 | Sprint 10 | 2027-01-11 | 2027-01-24 | 10 | Release & hypercare | 0 | 0 | 480 | 0% | Future
11 | Sprint 11 | 2027-01-25 | 2027-02-07 | 10 | Hypercare | 0 | 0 | 480 | 0% | Future
12 | Sprint 12 | 2027-02-08 | 2027-02-21 | 10 | Close-out | 0 | 0 | 480 | 0% | Future
13 |  | 2027-02-22 | 2027-03-07 | 10
14 |  | 2027-03-08 | 2027-03-21 | 10
15 |  | 2027-03-22 | 2027-04-04 | 10
16 |  | 2027-04-05 | 2027-04-18 | 10
17 |  | 2027-04-19 | 2027-05-02 | 10
18 |  | 2027-05-03 | 2027-05-16 | 10
19 |  | 2027-05-17 | 2027-05-30 | 10
20 |  | 2027-05-31 | 2027-06-13 | 10
21 |  | 2027-06-14 | 2027-06-27 | 10
22 |  | 2027-06-28 | 2027-07-11 | 10
23 |  | 2027-07-12 | 2027-07-25 | 10
24 |  | 2027-07-26 | 2027-08-08 | 10
25 |  | 2027-08-09 | 2027-08-22 | 10
26 |  | 2027-08-23 | 2027-09-05 | 10
Resource load by sprint (hours) - red = over capacity (Max Units x Hours/day x working days)
| Resource | Max Units | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12
| Sprint start |  | 2026-09-07 | 2026-09-21 | 2026-10-05 | 2026-10-19 | 2026-11-02 | 2026-11-16 | 2026-11-30 | 2026-12-14 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-02-08 | 2027-02-22 | 2027-03-08 | 2027-03-22 | 2027-04-05 | 2027-04-19 | 2027-05-03 | 2027-05-17 | 2027-05-31 | 2027-06-14 | 2027-06-28 | 2027-07-12 | 2027-07-26 | 2027-08-09 | 2027-08-23
| Sprint end |  | 2026-09-20 | 2026-10-04 | 2026-10-18 | 2026-11-01 | 2026-11-15 | 2026-11-29 | 2026-12-13 | 2026-12-27 | 2027-01-10 | 2027-01-24 | 2027-02-07 | 2027-02-21 | 2027-03-07 | 2027-03-21 | 2027-04-04 | 2027-04-18 | 2027-05-02 | 2027-05-16 | 2027-05-30 | 2027-06-13 | 2027-06-27 | 2027-07-11 | 2027-07-25 | 2027-08-08 | 2027-08-22 | 2027-09-05
| Priya Sharma | 50% | 2026-09-20: 24; 2026-10-04: 0; 2026-10-18: 0; 2026-11-01: 0; 2026-11-15: 0; 2026-11-29: 8; 2026-12-13: 0; 2026-12-27: 8; 2027-01-10: 16; 2027-01-24: 0; 2027-02-07: 0; 2027-02-21: 0
| Morgan Patel | 100% | 2026-09-20: 50.9091; 2026-10-04: 29.0909; 2026-10-18: 0; 2026-11-01: 0; 2026-11-15: 0; 2026-11-29: 0; 2026-12-13: 42; 2026-12-27: 6; 2027-01-10: 0; 2027-01-24: 0; 2027-02-07: 0; 2027-02-21: 0
| Alex Chen | 50% | 2026-09-20: 15; 2026-10-04: 25; 2026-10-18: 0; 2026-11-01: 0; 2026-11-15: 0; 2026-11-29: 0; 2026-12-13: 0; 2026-12-27: 0; 2027-01-10: 0; 2027-01-24: 0; 2027-02-07: 0; 2027-02-21: 0
| Casey Kim | 100% | 2026-09-20: 0; 2026-10-04: 37.3333; 2026-10-18: 10.6667; 2026-11-01: 0; 2026-11-15: 23.4286; 2026-11-29: 8.5714; 2026-12-13: 0; 2026-12-27: 0; 2027-01-10: 0; 2027-01-24: 0; 2027-02-07: 0; 2027-02-21: 0
| Jordan Lee | 100% | 2026-09-20: 0; 2026-10-04: 0; 2026-10-18: 60; 2026-11-01: 60; 2026-11-15: 48; 2026-11-29: 0; 2026-12-13: 0; 2026-12-27: 24; 2027-01-10: 16; 2027-01-24: 0; 2027-02-07: 0; 2027-02-21: 0
| Sam Rivera | 100% | 2026-09-20: 0; 2026-10-04: 0; 2026-10-18: 48; 2026-11-01: 74.6667; 2026-11-15: 21.3333; 2026-11-29: 0; 2026-12-13: 0; 2026-12-27: 0; 2027-01-10: 0; 2027-01-24: 0; 2027-02-07: 0; 2027-02-21: 0
| Taylor Morgan | 100% | 2026-09-20: 0; 2026-10-04: 0; 2026-10-18: 0; 2026-11-01: 0; 2026-11-15: 38.4; 2026-11-29: 25.6; 2026-12-13: 0; 2026-12-27: 0; 2027-01-10: 0; 2027-01-24: 0; 2027-02-07: 0; 2027-02-21: 0
Resource utilisation by sprint (%)
| Resource | Max Units | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12
| Priya Sharma | 50% | 60% | 0% | 0% | 0% | 0% | 20% | 0% | 25% | 50% | 0% | 0% | 0%
| Morgan Patel | 100% | 63.64% | 36.36% | 0% | 0% | 0% | 0% | 52.5% | 9.375% | 0% | 0% | 0% | 0%
| Alex Chen | 50% | 37.5% | 62.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Casey Kim | 100% | 0% | 46.67% | 13.33% | 0% | 29.29% | 10.71% | 0% | 0% | 0% | 0% | 0% | 0%
| Jordan Lee | 100% | 0% | 0% | 75% | 75% | 60% | 0% | 0% | 37.5% | 25% | 0% | 0% | 0%
| Sam Rivera | 100% | 0% | 0% | 60% | 93.33% | 26.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Taylor Morgan | 100% | 0% | 0% | 0% | 0% | 48% | 32% | 0% | 0% | 0% | 0% | 0% | 0%
Formulas:
End = [Start]+SprintLength-1
Working Days = NETWORKDAYS.INTL([Start],[End],WorkWeek,Holidays)

## Holidays
Holidays & Non-Working Days
Every date listed here is skipped by all scheduling formulas (named range: Holidays).
| Date | Description
| 2026-12-24 | Christmas Eve (example - replace with your calendar)
| 2026-12-25 | Christmas Day (example)
| 2026-12-31 | New Year's Eve (example)
| 2027-01-01 | New Year's Day (example)

## MSP_Tasks
ID | Name | Outline Level | Task Mode | Duration | Start | Finish | Predecessors | Resource Names | % Complete | Actual Start | Actual Finish | Baseline Start | Baseline Finish | Constraint Type | Constraint Date | Notes
1 | Initiation | 1 | Auto Scheduled |  | 2026-09-07 | 2026-09-14 | [5 empty] | 2026-09-07 | 2026-09-11 |  |  | Phase 1 - summary rows roll up dates, work, cost and progress automatically.
2 | Project charter & scope statement | 2 | Auto Scheduled | 3d | 2026-09-07 | 2026-09-10 |  | Priya Sharma | 100 | 2026-09-07 | 2026-09-10 | 2026-09-07 | 2026-09-09 | As Soon As Possible |  | Took 1 extra day for sponsor sign-off.
3 | Stakeholder kickoff workshop | 2 | Auto Scheduled | 2d | 2026-09-11 | 2026-09-14 | 2 | Morgan Patel | 100 | 2026-09-11 | 2026-09-14 | 2026-09-10 | 2026-09-11 | As Soon As Possible
4 | Kickoff complete | 2 | Auto Scheduled | 0d | 2026-09-14 | 2026-09-14 | 3 |  | 100 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | As Soon As Possible |  | Milestone (Duration 0).
5 | Requirements & Design | 1 | Auto Scheduled |  | 2026-09-15 | 2026-10-06 | [5 empty] | 2026-09-14 | 2026-10-01
6 | Requirements gathering | 2 | Auto Scheduled | 8d | 2026-09-15 | 2026-09-25 | 4 | Morgan Patel | 100 | 2026-09-15 | 2026-09-25 | 2026-09-14 | 2026-09-23 | As Soon As Possible
7 | Solution architecture | 2 | Auto Scheduled | 5d | 2026-09-18 | 2026-09-25 | 6SS+3d | Alex Chen | 100 | 2026-09-18 | 2026-09-25 | 2026-09-17 | 2026-09-23 | As Soon As Possible |  | Start-to-Start + 3 day lag example.
8 | UX wireframes & prototype | 2 | Auto Scheduled | 6d | 2026-09-28 | 2026-10-06 | 6 | Casey Kim | 100 | 2026-09-28 | 2026-10-06 | 2026-09-24 | 2026-10-01 | As Soon As Possible
9 | Design sign-off | 2 | Auto Scheduled | 0d | 2026-10-06 | 2026-10-06 | 7,8 |  | 100 | 2026-10-06 | 2026-10-06 | 2026-10-01 | 2026-10-01 | As Soon As Possible |  | Two predecessors - waits for the later one.
10 | Build | 1 | Auto Scheduled |  | 2026-10-07 | 2026-11-09 | [5 empty] | 2026-10-02 | 2026-10-30
11 | Backend | 2 | Auto Scheduled |  | 2026-10-07 | 2026-11-09 | [5 empty] | 2026-10-02 | 2026-10-30 |  |  | Level-2 summary with sub-tasks.
12 | Data model & database setup | 3 | Auto Scheduled | 5d | 2026-10-07 | 2026-10-14 | 9 | Jordan Lee | 100 | 2026-10-07 | 2026-10-14 | 2026-10-02 | 2026-10-08 | As Soon As Possible
13 | Core API endpoints | 3 | Auto Scheduled | 10d | 2026-10-15 | 2026-10-30 | 12 | Jordan Lee | 50 | 2026-10-15 |  | 2026-10-09 | 2026-10-22 | As Soon As Possible |  | In progress - enter % Complete; forecast finish adjusts.
14 | Payment gateway integration | 3 | Auto Scheduled | 6d | 2026-11-02 | 2026-11-09 | 13 | Jordan Lee | 0 |  |  | 2026-10-23 | 2026-10-30 | As Soon As Possible
15 | Frontend | 2 | Auto Scheduled |  | 2026-10-07 | 2026-11-06 | [5 empty] | 2026-10-02 | 2026-10-29
16 | UI component library | 3 | Auto Scheduled | 6d | 2026-10-07 | 2026-10-16 | 9 | Sam Rivera | 100 | 2026-10-07 | 2026-10-16 | 2026-10-02 | 2026-10-09 | As Soon As Possible
17 | Feature screens | 3 | Auto Scheduled | 12d | 2026-10-19 | 2026-11-05 | 16,13SS+2d | Sam Rivera | 25 | 2026-10-19 |  | 2026-10-13 | 2026-10-28 | As Soon As Possible
18 | Accessibility review | 3 | Auto Scheduled | 3d | 2026-11-04 | 2026-11-06 | 17FF+1d | Casey Kim[50%] | 0 |  |  | 2026-10-27 | 2026-10-29 | As Soon As Possible |  | Finish-to-Finish + 1 day; 50% units.
19 | Build complete | 2 | Auto Scheduled | 0d | 2026-11-09 | 2026-11-09 | 14,18 |  | 0 |  |  | 2026-10-30 | 2026-10-30 | As Soon As Possible |  | Milestone
20 | Test & Release | 1 | Auto Scheduled |  | 2026-11-10 | 2027-01-04 | [5 empty] | 2026-11-02 | 2027-01-04
21 | System integration testing | 2 | Auto Scheduled | 8d | 2026-11-10 | 2026-11-19 | 19 | Taylor Morgan | 0 |  |  | 2026-11-02 | 2026-11-11 | As Soon As Possible
22 | User acceptance testing | 2 | Auto Scheduled | 6d | 2026-12-07 | 2026-12-14 | 21 | Morgan Patel | 0 |  |  | 2026-12-07 | 2026-12-14 | Start No Earlier Than | 2026-12-07 | Start No Earlier Than 07-Dec (client availability).
23 | Training & user guides | 2 | Auto Scheduled | 5d | 2026-11-12 | 2026-11-18 | 21SS+2d | Casey Kim[50%] | 0 |  |  | 2026-11-04 | 2026-11-10 | As Soon As Possible
24 | Go-live readiness review | 2 | Auto Scheduled | 1d | 2026-12-15 | 2026-12-15 | 22,23 | Priya Sharma | 0 |  |  | 2026-12-15 | 2026-12-15 | As Soon As Possible
25 | Go-live | 2 | Auto Scheduled | 0d | 2026-12-15 | 2026-12-15 | 24 |  | 0 |  |  | 2026-12-15 | 2026-12-15 | As Soon As Possible |  | Milestone
26 | Hypercare support | 2 | Auto Scheduled | 10d | 2026-12-16 | 2027-01-04 | 25 | Jordan Lee[50%] | 0 |  |  | 2026-12-16 | 2027-01-04 | As Soon As Possible
27 | Project Close | 1 | Auto Scheduled |  | 2026-11-16 | 2027-01-06 | [5 empty] | 2026-11-16 | 2027-01-06
28 | Steering committee update | 2 | Manually Scheduled | 1d | 2026-11-16 | 2026-11-16 |  | Priya Sharma | 0 |  |  | 2026-11-16 | 2026-11-16 | As Soon As Possible |  | Manual mode example: fixed on the date in the Start No Earlier Than / Manual Start column.
29 | Lessons learned | 2 | Auto Scheduled | 2d | 2027-01-05 | 2027-01-06 | 26 | Priya Sharma | 0 |  |  | 2027-01-05 | 2027-01-06 | As Soon As Possible
30 | Project closed | 2 | Auto Scheduled | 0d | 2027-01-06 | 2027-01-06 | 29 |  | 0 |  |  | 2027-01-06 | 2027-01-06 | As Soon As Possible |  | Milestone

## MSP_Resources
Name | Initials | Group | Type | Max Units | Standard Rate | Email Address
Priya Sharma | PS | Project Manager | Work | 50% | 95/h | priya@example.com
Morgan Patel | MP | Business Analyst | Work | 100% | 70/h | morgan@example.com
Alex Chen | AC | Solution Architect | Work | 50% | 110/h | alex@example.com
Casey Kim | CK | UX Designer | Work | 100% | 75/h | casey@example.com
Jordan Lee | JL | Backend Developer | Work | 100% | 85/h | jordan@example.com
Sam Rivera | SR | Frontend Developer | Work | 100% | 80/h | sam@example.com
Taylor Morgan | TM | QA Engineer | Work | 100% | 65/h | taylor@example.com

## Lists
L_DepType | L_Mode | L_YesNo | L_ResType | L_Period
FS | Auto | Yes | Work | 1
SS | Manual | No | Material | 7
FF |  |  | Cost
SF
Dropdown sources. Add values to a list and extend its named range (Formulas > Name Manager).